## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Palla Zone-II W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000113/2021-2022 | 1174/NWSD-I | 31/12/2021 | 07/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 4.65 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 1210/NWSD-I | 13/10/2022 | 13/10/2022 | Resource Division | 0.04 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 458/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 229.11 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.35 | 6.67 | 100
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | New service connection at P.H.No- I ,Zone - II of Palla water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05852/2023-2024 | BP-386-23-24 | 28/03/2024 | 28/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.63 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Construction of approach road by jhama metal with allied works in front of Palla zone-II OHR site & Road Restoration within the command area under Palla Zone-II at Bongaon Block in the District of North 24 Pgs under North 24 Pgs W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000026/2025-2026 | 798/NWSD-I | 28/05/2025 | 23/01/2026 | M/S. TARAK CHANDRA PAUL | 15.46 | 0 | 0 | 75
7 | NORTH 24 PARGANAS |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Palla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas W/S Division-I,PHE Dte. | SM/10607 | Augmentation | Laying of Distribution System including specials & valves, pipe carrying structure all complete, Providing FHTC including supplying , laying, fitting, fixing of 15 mm NB PVC (Schedule 80) / 20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, construction of R.C.C Elevated Reservoir 500m3,Construction of Boundary wall at H/W site, pump house (4.88M x 3.66M) including sanitary arrangement, Service Road (60Mtr. Length x 3 Mtr. Width) at Head Work site for Palla Zone - II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000077/2023-2024 | 991/NWSD-I | 24/07/2023 | 01/11/2026 | M/S. TARAK CHANDRA PAUL | 703.14 | 224.08 | 31.87 | 2
Total | [13 empty] | 22304.07 | 229.08 | 1.03