## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household under Paikpara Zone-I W/S scheme in North 24 Pgs. District under North 24 Pgs. W/S Sub-Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000109/2021-2022 | 1171/NWSD-I | 31/12/2021 | 07/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.81 | 4.81 | 100 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system and Providing Functional House Hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC , Schedule 80/20 mm OD HDPE (PE 100, PN16) pipe with all necessary works within command area of PAIKPARA ZONE-I Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000056/2022-2023 | 1086/NWSD-1 | 09/09/2022 | 26/05/2026 | CONCORD ENGINEERING | 556.79 | 429.39 | 77.12 | 70
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 1165/NWSD-I | 26/09/2022 | 26/09/2022 | Resource Division | 0.03 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Repair and renovation works of 1000 m3 RCC Elevated Reservoir, Boundary Wall, Pump House, Service roads etc. at Head Works Site and other tube well Sites under Paikpara Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000137/2022-2023 | 235/NWSD-I | 02/03/2023 | 18/08/2025 | SUDHAMAY MAJUMDAR | 76.43 | 0 | 0 | 55
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV (Zone-I) (Rep) under Paikpara W/S Scheme District of 24 Pgs. (N) |  |  | ORD/001138/2023-2024 | 4740/EMD | 07/08/2023 | 06/09/2023 | CINZANO | 26.54 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Paikpara W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001139/2023-2024 | 4741/EMD | 07/08/2023 | 06/09/2023 | S.P. ENTERPRISE (SILIGURI) | 26.24 | 15.18 | 57.87 | 66
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1840/NWSD-I | 10/11/2023 | 10/11/2023 | Resource Division | 3.08 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0 | 0 | 100
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 1307/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 6.16 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Paikpara Zone-I Water SupplyScheme in Bongaon Block of North 24 Parganas District under N 24 Pgs. W/S Div-I, PHE Dte. | SM/10638 | Augmentation | Construction of Bituminous road from Ghatbour GP office to Kalmegha at Ghatbour GP under Bongaon Block. |  |  | BILL/00245/2024-2025 | 279/PFMS/24-25 | 06/12/2024 | 06/12/2024 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 15.51 | 0 | 0 | 0
Total | [13 empty] | 725.47 | 449.38 | 61.94