## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with Providing functional household tap connection to every Household with in Khamarkalla (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000129/2021-2022 | 1188/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.88 | 4.88 | 100 | 1
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 434/NWSD-I | 24/04/2023 |  | Resource Division | 146.23 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1838/NWSD-I | 10/11/2023 |  | Resource Division | 3.08 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-I) (Rep) under Khamarkalla W/S Scheme District of 24 Pgs. (N) | Assistant Engineer | Junior Engineer | ORD/001142/2023-2024 | 4745/EMD | 07/08/2023 | 06/09/2023 | ALAK KUMAR CHAKRABORTY | 26.5 | 15.53 | 58.58 | 65
5 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Laying of Distribution pipe line and Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe including all necessary works at distribution system within command area of Khamarkalla Zone-I Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000078/2022-2023 | 1289/NWSD-I | 07/11/2022 | 05/02/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 527.02 | 489.08 | 92.8 | 100
6 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Repair and renovation works for 1000 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall, Pump House at H/W site and PH-II , III & IV with other allied works at Khamarkhalla (Z-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000110/2023-2024 | 1263/NWSD-I | 21/08/2023 | 20/10/2023 | M/S. TARAK CHANDRA PAUL | 66.2 | 20.64 | 31.17 | 100
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.III and IV (Zone-I) (Rep) under Khamarkalla W/S Scheme District of 24 Pgs. (N) NIET No. 27 of EE/EMD of 2022-2023 (Sl. No. 25) |  |  | ORD/001904/2023-2024 | 6772/EMD | 29/11/2023 | 29/12/2023 | BOSE & CHATTERJEE INDUSTRIES | 26.47 | 0 | 0 | 0
8 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of Augmentation for Khamarkalla Zone-I Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Pgs. W/S. Division-I, PHE. Dte. | SM/10639 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 1305/NWSD-I | 30/08/2024 |  | Resource Division | 3.08 | 0 | 0 | 0
Total | [13 empty] | 803.46 | 530.12 | 65.98