## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bilkanda Zone-I Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bilkanda Zone-I W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000194/2020-2021 | 451/NWSD-I | 10/06/2020 | 13/06/2020 | RAKESH ENTERPRISE | 0.97 | 0.95 | 98.21 | 100
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Auldanga Water Supply Scheme of Bagdah Block under North 24 Parganas Water Supply Division-I P.H.E. Dte. Location : Within Auldanga W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000190/2020-2021 | 438/NWSD-I | 08/06/2020 | 11/06/2020 | ONKAR ENTERPRISE | 4.78 | 4.78 | 100 | 100
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Ichhlampur Zone-I Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location : Within Ichhlampur Zone-I W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000191/2020-2021 | 406/NWSD-I | 27/05/2020 | 30/05/2020 | OM CONSTRUCTION | 2.77 | 2.76 | 99.56 | 100
4 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Palla Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Palla W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000196/2020-2021 | 427/NWSD-I | 05/06/2020 | 08/06/2020 | M/S. R. M. CONSTRUCTION | 3.13 | 3.13 | 100 | 100
5 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bilkanda Zone-II Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bilkanda Zone-II W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000195/2020-2021 | 441/NWSD-I | 08/06/2020 | 11/06/2020 | B. S. ENTERPRISE | 1.97 | 1.97 | 99.89 | 100
6 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Barakpur Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Barakpur W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000188/2020-2021 | 440/NWSD-I | 08/06/2020 | 11/06/2020 | OM CONSTRUCTION | 3.06 | 3.05 | 99.75 | 100
7 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Ichhlampur Zone-II Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Ichhlampur Zone-II W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000189/2020-2021 | 402/NWSD-I | 27/05/2020 | 30/05/2020 | OM CONSTRUCTION | 3.12 | 3.1 | 99.62 | 100
8 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Paikpara Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Paikpara W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000186/2020-2021 | 405/NWSD-I | 27/05/2020 | 30/05/2020 | SHAMALI ENTERPRISE | 1.82 | 1.82 | 100 | 100
9 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMHPAN on 20.05.2020 of Bagangram Zone-I Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000187/2020-2021 | 428/ NWSD-I | 06/06/2020 | 09/06/2020 | GHOSH CONSTRUCTION | 2.9 | 2.9 | 100 | 100
10 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Santoshpur Zone-II Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Santoshpur Zone-II W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000197/2020-2021 | 404/NWSD-I | 27/05/2020 | 30/05/2020 | B. S. ENTERPRISE | 2.25 | 2.25 | 99.83 | 100
11 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Boyra Water Supply Scheme of Bagdah Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Boyra W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000198/2020-2021 | 437/NWSD-I | 08/06/2020 | 11/06/2020 | B. S. ENTERPRISE | 1.78 | 1.78 | 100 | 100
12 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Khamarkalla Water Supply Scheme of Bongaon Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Khamarkalla W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000199/2020-2021 | 413/NWSD-I | 29/05/2020 | 01/06/2020 | B. S. ENTERPRISE | 3.01 | 3.01 | 100 | 100
13 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Suppply of drinking water by TATA 107/207/Mechanized van with tank from nearest source to different places of Khejurdanga, Keyadanga, Ajijnagore, Alipur & Uttar Kolsur under Deganga block from 22/05/2020 to 29/05/2020 due to 'AMPHAN' under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Deganga Block | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000200/2020-2021 | 397/NWSD-.I | 27/05/2020 | 30/05/2020 | SHAMALI ENTERPRISE | 1.79 | 1.78 | 99.72 | 100
14 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bandipur Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000193/2020-2021 | 450/NWSD-I | 10/06/2020 | 13/06/2020 | M/S SAIN ENTERPRISE | 2.25 | 2.24 | 99.85 | 100
15 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Teghari Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Teghari W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000201/2020-2021 | 442/NWSD-1 | 08/06/2020 | 11/06/2020 | A.K.C. SUPPLY & CONSTRUCTION | 2 | 1.29 | 64.63 | 100
16 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | SPECIAL REPAIRING WORK FOR THE DAMAGE CAUSED BY SUPER CYCLONE 'AMPHAN' ON 20.05.2020. AT DIFFERENT WATER SUPPLY SCHEME AT DEGANGA, BARRACKPORE-II, BONGAON & BAGDAH BLOCKS UNDER NORTH 24-PGS. WATER SUPPLY DIVISION-I, PHE DTE (PHASE-I) | SM/10757 | Disaster | Special repairing work for the damage caused by Cyclone AMPHAN on 20.05.2020 of Bandipur- Patulia (Rej) Water Supply Scheme of Barrackpur-II Block under North 24 Parganas Water Supply Division-I P.H.E.Dte. Location: Within Bandipur- Patulia (Rej) W/S Scheme. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000202/2020-2021 | 463/NWSD-1 | 15/06/2020 | 18/06/2020 | A.K.C. SUPPLY & CONSTRUCTION | 2.05 | 2.04 | 99.52 | 100
Total | [13 empty] | 39.65 | 38.87 | 98.03