## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Khamarkalla (Zone-II) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000127/2021-2022 | 1189/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.15 | 4.15 | 100 | 0
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 1209/NWSD-I | 13/10/2022 | 13/10/2022 | Resource Division | 0.04 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 456/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 23.57 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.18 | 3.33 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2024-2025 | 1304/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 12.32 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) by augmentation for Khamarkalla Zone-II Water Supply Scheme in Bongaon Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, P.H.E Dte. | SM/10758 | Augmentation | Laying of Distribution System including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for Khamarkalla Zone-II in Bongaon Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000169/2023-2024 | 1680/NWSD-I | 30/10/2023 | 27/04/2026 | MITRA CONSTRUCTION | 517.31 | 43.99 | 8.5 | 20
Total | [13 empty] | 562.66 | 48.31 | 8.59