## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 48 m Length in 3rd. Pump house site at Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000009/2023-2024 | 405/NWSD-I | 11/04/2023 | 26/05/2023 | SHAMALI ENTERPRISE | 5.9 | 3.55 | 60.24 | 70
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Mollahati Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000126/2021-2022 | 1191/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5 | 5 | 100 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Special Repairing & Renovation of Pump House at 2nd Pump House site & Service road (25 Mtr. Length X 2 Mtr. Width) at 2nd Pump House site of Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000011/2023-2024 | 407/NWSD-I | 11/04/2023 | 26/05/2023 | RAHUL ENTERPRISE | 4.13 | 3.6 | 87 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Special Repairing & Renovation of Pump House at Head Works site & Service road (60 Mtr. Length X 3 Mtr. Width) at Head works site of Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000010/2023-2024 | 406/NWSD-I | 11/04/2023 | 26/05/2023 | HAKIM ENTERPRISE | 7.29 | 6.93 | 95.08 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 51 m Length in 2nd Pump house site at Mollahati Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000014/2023-2024 | 413/NWSD-I | 11/04/2023 | 26/05/2023 | M/S SAIN ENTERPRISE | 6.19 | 4.01 | 64.83 | 60
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | UPVC pipe laying work along with allied works under Mollahati Water Supply Scheme in the district of North 24 PGS under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000088/2023-2024 | 1087/NWSD-I | 01/08/2023 | 30/09/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 76.32 | 76.25 | 99.91 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 1164/NWSD-I | 26/09/2022 | 26/09/2022 | Resource Division | 0.04 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Renovation of AIRP at Mollahati Water Supply Scheme of capacity 110.81 Cu.m/hr of Bongaon Block under North 24 Pgs. W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000059/2024-2025 | 1644/NWSD-I | 13/11/2024 | 12/05/2025 | CONCORD ENGINEERING | 71.75 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Mollahati Water Supply Scheme under district North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000057/2022-2023 | 1055/NWSD-I | 01/09/2022 | 30/11/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 681.95 | 678.05 | 99.43 | 100
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Repair and renovation works for 550 cum. capacity 20 mtr. staging height R.C.C. Over Head water Reservoir , Boundary wall at H/W site and PH-III with other allied works at Mollahati W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000111/2023-2024 | 1240/NWSD-I | 18/08/2023 | 17/10/2023 | MONDAL ENTERPRISE | 36.59 | 35.6 | 97.29 | 100
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.35 | 6.67 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Reimbursement of additional GST due to enhancement of rate from 12% to 18% vide Notification No. 03/2022 Central tax rate dt.13/07/2022 for the work of "Laying of distribution pipeline including providing FHTC at Mollahati W/S Scheme under NWSD-I, P.H.E. Dte. Tender No.82/eT/NWSD-I of 2022-23, Work Order No.1055/NWSD-I dt.01/09/2022, Enhancement GST Sanction No. PHE/IV/3260/W-698/23 dt.19/10/2023. |  |  | BILL/00126/2024-2025 | 180/PFMS/24-25 | 03/09/2024 | 03/09/2024 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 35.98 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) By augmentation for Mollahati Water Supply Scheme in Bongaon Block of North 24 Parganas District | SM/10777 | Augmentation | Laying of pipe line & special measure for protection of road and other allied works at different location under Augmentation work at Mollahati W/S. Scheme in Bongaon Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000067/2024-2025 | 51/NWSD-I | 09/01/2025 | 24/01/2025 | SUN ENTERPRISE | 4.73 | 0 | 0 | 100
Total | [13 empty] | 941.17 | 813.35 | 86.42