## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Detail route Survey, Design and preparation of Augmentation DPR in connection with " Providing functional household tap connection to every Household with in Ichhlampur (Zone-I) Water Supply Scheme in North 24 Pgs. District under North 24 Pgs. W/S. Division-I P.H.E. Dte." | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000139/2021-2022 | 1186/NWSD-I | 31/12/2021 | 15/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.65 | 4.65 | 100 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Providing And Installation of Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at Zone I of Ichhlampore Piped Water Supply Scheme, Block Bongaon Dist. North 24 Pgs under EMD, PHE Dte. |  |  | ORD/001213/2023-2024 | 4871/EMD | 14/08/2023 | 13/09/2023 | DIPALI CONSTRUCTION | 37.15 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying, laying, fitting, fixing of 15 mm NB PVC, schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works including proposed Rising Main system within command area of Ichhlampur Zone-1 Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000050/2022-2023 | 876/NWSD-I | 22/07/2022 | 20/10/2022 | M/S. TARAK CHANDRA PAUL | 763.75 | 680.99 | 89.16 | 62
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 160 m Length in Head work site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000006/2023-2024 | 380/NWSD-I | 05/04/2023 | 20/05/2023 | ROY CHOWDHURY CONSTRUCTION | 16.26 | 8.16 | 50.16 | 75
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 45 m Length in 3rd Pump house site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000007/2023-2024 | 382/NWSD-I | 05/04/2023 | 20/05/2023 | A K DUTTA & CO | 6.05 | 5.78 | 95.49 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Repairing & Renovation of BOUNDARY WALL for 45 m Length in 2nd Pump house site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000008/2023-2024 | 381/NWSD-I | 05/04/2023 | 20/05/2023 | M/S DHELA BABA ENTERPRISE | 6.08 | 4 | 65.81 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Special Repair & Renovation two nos. Pump house and Servicer road at 2nd & 3rd Tube well site at Ichhlampur Zone-I Water Supply scheme in Bongaon Block under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000041/2023-2024 | 881/NWSD-I | 12/07/2023 | 26/08/2023 | MAA TARA ENTERPRISE | 8.64 | 6.34 | 73.38 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 880/NWSD-I | 22/07/2022 | 22/07/2022 | Resource Division | 75.43 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 879/NWSD-I | 22/07/2022 | 22/07/2022 | Resource Division | 28.08 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 105 cum/hr at Head work site of Ichhlampur (Zone-I) Water Supply Scheme within the Bongaon Block and other anciliary work under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000367/2023-2024 | 499/NWSD-I | 15/03/2024 | 15/03/2025 | HARBAUER INDIA (P) LTD | 267.95 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Repair and renovation works for 550 cum. capacity R.C.C. Over Head water Reservoir and other allied works at Ichhlampur (Zone-I) W/S Scheme under North 24 Pgs Water Supply Division- I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000150/2023-2024 | 1436/NWSD-I | 11/09/2023 | 10/11/2023 | ROY CHOWDHURY CONSTRUCTION | 27.71 | 27.03 | 97.56 | 100
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 1312/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 1.85 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Laying of distribution system including specials ,valves, & pipes carrying all complete at Ichhlampur Zone-I Water Supply scheme in the District of North 24 Parganas under North 24 Parganas water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000038/2024-2025 | 1628/NWSD-I | 12/11/2024 | 07/01/2026 | M/S. S.S. ENTERPRISE | 23.57 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR ICHHLAMPUR ZONE-I WTO ACCOMMODATE FHTC IN BONGAON BLOCK OF NORTH 24 PARGANAS DISTRICT UNDER N 24 PGS. W/S. DIV-I, PHE. DTE. | SM/11214 | Augmentation | Supply and installation of 26 (Twenty-Six) Nos. Display Board for information regarding "SWAJAL GRAM", to be placed at different locations for Bagda, Bongaon, Barrackpore -II & Barasat-I Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000025/2024-2025 | 1431/NWSD-I | 18/09/2024 | 25/09/2024 | IMAGIN | 4.59 | 0 | 0 | 95
Total | [13 empty] | 1271.77 | 736.95 | 57.95