## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Barbaria of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000013/2022-2023 | 431/NWSD-I | 01/04/2022 | 15/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.95 | 3.95 | 100 | 1
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Repairing of unmanned panel by supplying of different electrical spares at P.H I under Barberia W/s scheme |  |  | ORD/000322/2021-2022 | 1695/EMSD I | 02/07/2021 | 19/07/2021 | TAMAL ENTERPRISE | 0.16 | 0.16 | 100 | 1
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. depth at 2nd Tube Well site within command area of Barbaria Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000099/2022-2023 | 1342/NWSD-I | 22/11/2022 | 12/12/2022 | SAHA CONSTRUCTION & CO. | 20.97 | 14.66 | 69.91 | 1
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Sinking of 01 No. Tube well 300 x 200 mm dia, 300 mtr. depth at Head Works site within command area of Barbaria Water Supply Scheme under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000098/2022-2023 | 1340/NWSD-I | 22/11/2022 | 12/12/2022 | SUDHAMAY MAJUMDAR | 20.97 | 15.1 | 71.99 | 1
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Site development, construction of Approach road, Bank potection by bullah piling and other ancillary works at Head work site of Barbaria water supply scheme and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000139/2023-2024 | 1398/NWSD-I | 05/09/2023 | 04/11/2023 | M/S. SHUBHA ENTERPRISE | 18.04 | 17.45 | 96.7 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2023-2024 | 468/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 36.83 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I and II (Zone-II) (Rep.) under Kanaikathi-Kanthalberia W/S Scheme and Barberia W/S Scheme District of 24 Pgs. (N) NIET No.- 32 of EE/EMD of 2022-23 (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/001972/2022-2023 | 1286/EMD | 28/03/2023 | 01/10/2024 | BENGAL CONSTRUCTION | 54.33 | 0 | 0 | 50
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Construction of boundary wall at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000022/2024-2025 | 1217/NWSD-I | 16/08/2024 | 30/09/2024 | DAS TRADING | 8.01 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Construction of Service Road at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000020/2024-2025 | 1219/NWSD-I | 16/08/2024 | 31/08/2024 | OM CONSTRUCTION | 2.67 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Special Repair & Renovation , Construction of Boundary Wall and other ancilliary works under Augmentation of Ground water based Barbaria water supply scheme of North 24 Parganas District under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000149/2023-2024 | 1435/NWSD-I | 11/09/2023 | 10/11/2023 | ELIJA CONSTRUCTION | 11.61 | 8.32 | 71.69 | 100
11 | NORTH 24 PARGANAS |  | Eastern Mechanical | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | New service connection at P.H.No- I, Zone-II of Barberia water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05529/2023-2024 | BP-347-23-24 | 21/03/2024 | 21/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.32 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Laying of Distribution pipe line including all necessary works at distribution system & Providing Functional House hold Tap Connection (FHTC) including supplying,laying, fitting, fixing of 15 mm NB PVC, Schedule 80/20 mm OD HDPE (PE 100, PN 16) pipe with all necessary works within command area of Barbaria Water Supply Scheme & adjoinings mouzas under Barasat-I block in the district of North 24 Parganas under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000080/2022-2023 | 1331/NWSD-I | 18/11/2022 | 16/02/2023 | SUDHAMAY MAJUMDAR | 159.95 | 60.78 | 38 | 40
13 | NORTH 24 PARGANAS |  | Central Drilling | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 21.62 | 0.1 | 11
14 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Providing FHTC (Functional Household Tap Connection) of augmentation for Barbaria Water Supply Scheme in Barasat-I Block of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. | SM/11556 | Augmentation | Construction of Iron elimination Plant (IEP) with concrete Platform, drain etc. at 3rd T/W site of Barbaria Water Supply Scheme under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000019/2024-2025 | 1420/NWSD-I | 17/09/2024 | 11/12/2025 | NEER UDYOG | 19.51 | 0 | 0 | 49
Total | [13 empty] | 21702.08 | 142.04 | 0.65