## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-II/B (Malikapur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | ORD/000200/2021-2022 | 331/NWSD-I | 24/03/2022 | 24/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.29 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. |  |  | ORD/001058/2023-2024 | 4029/ED | 17/10/2023 | 17/04/2024 | A.G. ENTERPRISE | 55.55 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 480/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 31.12 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Payment to WBSEDCL of Malikapur |  |  | BILL/01116/2023-2024 |  | 27/06/2023 | 27/06/2023 | WBSEDCL | 1.66 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Quotation for New Connection at Malikapur OHR site. |  |  | BILL/02478/2024-2025 | 609 | 05/12/2024 | 05/12/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Shifting of HTOH & LTOH line from PHE Land. Application ID: 100000118529 Application Date: 09.09.2024 Quotation Date: 09.09.2024 Quotation due date: 08.12.2024 |  |  | BILL/00158/2024-2025 | 204/PFMS/24-25 | 19/09/2024 | 19/09/2024 | WBSEDCL | 1.9 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II-B (Malikapur) in Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11864 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
Total | [13 empty] | 21497.46 | 0 | 0