## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11971 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VIII/C (Pasardanga) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000011/2022-2023 | 430/NWSD-I | 01/04/2022 | 15/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.17 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11971 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 482/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 45.06 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11971 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 1714/NWSD-I | 26/11/2024 | 26/11/2024 | Resource Division | 10.47 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VIII-C (Pasardanga) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/11971 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
Total | [13 empty] | 21459.7 | 0 | 0