## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VI/B (Tapanpur) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000203/2021-2022 | 334/NWSD-I | 24/03/2022 | 24/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.33 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. |  |  | ORD/001061/2023-2024 | 4032/ED | 17/10/2023 | 17/04/2024 | ALPHA ENTERPRISE | 58.67 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 487/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 163.65 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2024-2025 | 1716/NWSD-I | 26/11/2024 | 26/11/2024 | Resource Division | 14.78 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Shifting of HTOH Pole at Tapanpur , Amdanga Block . |  |  | BILL/00106/2024-2025 | 132/PFMS/24-25 | 30/07/2024 | 30/07/2024 | WBSEDCL | 0.63 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-B (Tapanpur) in Amdanga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12372 | Augmentation | Road restoration along flank portion of Rafipur Padmanavpur Kakinara PWD road, Sani Mandir (Node 481 ) to Tapanpur F.P School (Node - 30) due to laying of pipeline under Augmentation work at Tapanpur (Zone- VI B) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000020/2025-2026 | 776/NWSD-I | 23/05/2025 | 07/07/2025 | SAHA CONSTRUCTION & CO. | 44.17 | 0 | 0 | 0
Total | [13 empty] | 21686.23 | 0 | 0