## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-VI/A (Beraberia) of Surface based Water Supply Scheme for Arsenic affected areas of N 24 Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 1 | ORD/000202/2021-2022 | 333/NWSD-I | 24/03/2022 | 25/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.96 | 102.67 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 214.68 | 1 | 2
3 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001056/2023-2024 | 4028/ED | 17/10/2023 | 17/04/2024 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 0 | 10
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 471/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 157.98 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2024-2025 | 1707/NWSD-I | 26/11/2024 | 26/11/2024 | Resource Division | 10.16 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Madhabpur to Harpara Dakshin Package No. WB-01-336 due to laying pipi line. |  |  | BILL/00172/2024-2025 | 218/PFMS/24-25 | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER, WBSRDA, NORTH 24 PARGANAS DIVISION | 13.5 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI-A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/12566 | Augmentation | Road restoration along flank portion of Rafipur Padmanavpur Kakinara PWD road, Madhavpur High School (Node 563) to Dishari Adarsha Siksha Niketan (Node - 804) due to laying of pipeline under Augmentation work at Beraberia (Zone- VI A) W/S Scheme in Amdanga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000021/2025-2026 | 777/NWSD-I | 23/05/2025 | 22/06/2025 | AREOCON | 12.54 | 0 | 0 | 0
Total | [13 empty] | 21632.18 | 219.65 | 1.02