## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IV/B (Saraberia) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000008/2022-2023 | 423/NWSD-I | 01/04/2022 | 15/04/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.87 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 485/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 78.35 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Way leave / crossing purpose water supply (JJM) station from Kazipara Halt to Karea Kadambagachhi Halt. (Eastern Railway, Sealdah). KM Mast : 4/35-37 - 4/34-36, Application ID : ER-SDAH-2023-WL-56 |  |  | BILL/00257/2023-2024 | 261/PFMS/23-24 | 03/10/2023 | 03/10/2023 | EASTERN RAILWAY, SEALDAH | 6.22 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Way leave / crossing purpose water supply (JJM) station from Kazipara Halt to Karea Kadambagachi. (Eastern Railway, Sealdah). KM Mast : 6/02-06 - 6/01-05, Application ID : ER-SDAH-2023-WL-57. |  |  | BILL/00258/2023-2024 | 262/PFMS/23-24 | 03/10/2023 | 03/10/2023 | EASTERN RAILWAY, SEALDAH | 4.74 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Railway way leave permission between Mast 6/02-06 - 6/01-05 at Station from Kazipara Halt (KZPR)- Karea Kadambagachhi Halt (KBGH) for laying 600 mm. dia. (OD) M.S pipe by Jack Pushing Technique for Augmentaion of Surface Based Piped Water Supply Scheme for Zone- IV-B (Saraberia) in Barasat-I Block under North 24 Pgs W/S Division-I P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000272/2023-2024 | 2126/NWSD-I | 28/12/2023 | 28/01/2024 | M/S. SHUBHA ENTERPRISE | 0.95 | 0 | 0 | 100
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 1715/NWSD-I | 26/11/2024 | 26/11/2024 | Resource Division | 17.86 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 0 | 0 | 2
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-IV-B (Saraberia) in Barasat-I Block of North 24 Parganas District under North 24 Parganas W/S Division-I, PHE Dte. | SM/12625 | Augmentation | Reapiring and restoration of Black Top metal road under the command area of Saraberia, Kharki, Tentulia Water Supply Scheme within Barasat-I Block under North 24 Pgs W/S Division-I | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000030/2025-2026 | 754/NWSD-I | 22/05/2025 | 06/07/2025 | BASHUDEV DUTTA | 45.91 | 0 | 0 | 0
Total | [13 empty] | 21558.91 | 0 | 0