## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-XII (Abjannagar) under North 24 Pgs. W/S Division-I, P.H.E. Dte. Sl.No. - 12. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000070/2022-2023 | 1298/NWSD-I | 07/11/2022 | 21/11/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.49 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 459/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 128.89 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of ZONE-XII (ABJANNAGAR) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000172/2023-2024 | 1619/NWSD-I | 12/10/2023 | 11/10/2024 | A.K.C. SUPPLY & CONSTRUCTION | 567.97 | 0 | 0 | 45
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000026/2024-2025 | 1432/NWSD-I | 18/09/2024 | 02/10/2024 | S M TRADERS | 2.17 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 1316/NWSD-I | 30/08/2024 | 30/08/2024 | Resource Division | 17.11 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | New service connection at P.H.No- I , Zone- XII of Abjannagar water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : |  |  | BILL/05018/2023-2024 | BP-340-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.41 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Driller In Charge | Junior Engineer | ORD/000060/2024-2025 | 24/CMSD-II(D) | 31/01/2025 | 01/08/2025 | MD NIZAMUDDIN | 0.86 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Laying of Pipeline & special measure for protection of road and other allied works at different location under Augmentation work at Abjannagar W/S. Scheme in Deganga Block under North 24 Pgs. W/S. Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000017/2025-2026 | 726/NWSD-I | 19/05/2025 | 18/06/2025 | A.K.C. SUPPLY & CONSTRUCTION | 67.06 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XII (Abjannagar) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13435 | Augmentation | Continuation for Hiring of Diesel Driven Motor cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mechanical Sub Division-ll (D),CDD, P.H.Enginering Dte. for supervision of JJM Related works. | Driller In Charge | Junior Engineer | ORD/000033/2025-2026 | 152/CMSD-II(D) | 30/07/2025 | 28/01/2026 | MD NIZAMUDDIN | 0.86 | 0 | 0 | 0
Total | [13 empty] | 22138.59 | 0 | 0