## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | Augmentation | Route Survey, Design Drawing & DPR Preparation for Zone-IB (Telinipara) of Surface based Water Supply Scheme for Arsenic affected areas of N24Pgs District under North 24 Pgs Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 1 | ORD/000201/2021-2022 | 332/NWSD-I | 24/03/2022 | 25/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.83 | 4.98 | 102.91 | 1
2 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. |  |  | ORD/001062/2023-2024 | 4033/ED | 17/10/2023 | 17/04/2024 | S.P. CONSTRUCTION | 34.15 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 488/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 85.47 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | Augmentation | Supply and installation of Display Board to be placeed at BILKANDA ZONE-I, BANDIPUR, BILKANDA ZONE-II, PATULIA and MOHANPUR, Zone-I-B (Telinipara), Zone-IA-II (Chak Kanthalia) pipe water supply scheme for Barrackpore-II Block under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000275/2023-2024 | 70/NWSD-I | 10/01/2024 | 09/02/2024 | BIBHAS PAL | 4.94 | 0.7 | 14.19 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I-B (Telinipara) in Barrackpore-II Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/13902 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 241.18 | 1.13 | 2
Total | [13 empty] | 21529.4 | 246.85 | 1.15