## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (BALIBHARA Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000117/2022-2023 | 120/NWSD-I | 02/02/2023 | 17/02/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.04 | 0 | 0 | 1
2 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 448/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 26.75 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Construction of Arsenic cum Iron removal Plants (AIRP) of capacity 70 cum/hr at Head work site of Balibhara Water Supply Scheme within the Barrackpore-I Block and other anciliary work under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000364/2023-2024 | 488/NWSD-I | 15/03/2024 | 11/09/2024 | PUSPA ENTERPRISE | 209.81 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0 | 0 | 100
5 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 27/NWSD-I | 04/01/2024 | 04/01/2024 | Resource Division | 15.04 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Barrackpur-I | Electrical | Balibhara Piped Water Supply Scheme | SM/14498 | New | Quotation for Balibhara w/s scheme TW no.- I |  |  | BILL/00449/2024-2025 | 116 | 17/05/2024 | 17/05/2024 | WBSEDCL | 4.33 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Barrackpur-I | Central Drilling | Balibhara Piped Water Supply Scheme | SM/14498 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Balibhara Piped Water Supply Scheme | SM/14498 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for BALIBHARA in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000167/2023-2024 | 1620/NWSD-I | 12/10/2023 | 02/04/2025 | A.K.C. SUPPLY & CONSTRUCTION | 535.19 | 0 | 0 | 48
Total | [13 empty] | 22143.21 | 0 | 0