## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | New | Laying of Distribution System, Rising Main including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir with pile foundation and pipe connection including cost of pipes & specials with soil investigation, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement Of Land, Pipe carring structure for a span of 25 Meter for crossing of a Canal / River etc. for Augmentation of Ground Water Based Piped Water Supply Scheme for KAUGACHHI ZONE-II in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000179/2023-2024 | 1679/NWSD-I | 30/10/2023 | 29/10/2024 | NOVELTY ENTERPRISE | 487.91 | 0 | 0 | 0
2 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (KAUGACHHI ZONE-II Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000119/2022-2023 | 122/NWSD-I | 02/02/2023 | 17/02/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.49 | 6.49 | 100 | 1
3 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 452/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 47 | 0 | 0 | 0
4 | NORTH 24 PARGANAS | Barrackpur-I | Central Drilling | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
5 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Kaugachhi Zone-II Piped Water Supply Scheme | SM/14500 | New | Shinking of 1 no. Tube well 300mm X 200mm Big Dia.Tube well 300 Mtr. Deep by Direct Rotary Rig method using PVC pipe & UPVC deep well screen pipes with ribs etc. Including cost of Materials for Kaugachi Zone-II Water Supply Scheme ( H/W site ) under North 24 Parganas wate supply Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000211/2024-2025 | 432/NWSD-I | 19/03/2025 | 18/04/2025 | B.K. ENTERPRISE | 22.7 | 0 | 0 | 0
Total | [13 empty] | 21903.86 | 6.49 | 0.03