## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Survey, Design Drawing & DPR Preparation for NEW PWSS (BIDYADHARPUR & ITS ADJOINING MOUZAS Water Supply Scheme) in BARRACKPUR-I BLOCK under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER 2 | ORD/000125/2022-2023 | 49/NWSD-I | 11/01/2023 | 26/01/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.91 | 0.91 | 100 | 1
2 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 449/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 0.38 | 0 | 0 | 0
3 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Laying of Distribution System including specials, valves and pipe carrying structure, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, Construction of Pump House (4.88m X 3.66m) including Sanitary Arrangement, Construction of Boundary Wall, Construction of Service Road, Improvement of Land, for Augmentation of Ground Water Based Piped Water Supply Scheme for Bidyadharpur & its Adjoining Mouzas in Barrackpur-I Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000168/2023-2024 | 1594/NWSD-I | 10/10/2023 | 08/01/2024 | DAS TRADING | 56.49 | 28.3 | 50.1 | 32
4 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Supply and installation of 30 (Thirty) Nos. Display Board for information to be placed at different locations for Bagda, Barrackpore -I & Bongaon Block Pipe Water Supply Scheme under North 24 Pgs. Water Supply Division-I , PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000024/2024-2025 | 1430/NWSD-I | 18/09/2024 | 25/09/2024 | BIBHAS PAL | 5.27 | 0.18 | 3.33 | 100
5 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 50/NWSD-I | 08/01/2024 | 08/01/2024 | Resource Division | 0.79 | 0 | 0 | 0
6 | NORTH 24 PARGANAS | Barrackpur-I | Electrical | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Quotation for new service connection at Bidyadharpur W/S Scheme PH No 1 ( SM/14501 ) |  |  | BILL/00110/2024-2025 | 34 | 09/04/2024 | 09/04/2024 | WBSEDCL | 0.79 | 0 | 0 | 0
7 | NORTH 24 PARGANAS | Barrackpur-I | North 24 Pgs W/S Division I | Bidyadharpur & its Adjoining Mouzas Piped Water Supply Scheme under North 24 Parganas W/S Division-I, PHE Dte. | SM/14501 | New | Laying of pipeline & special measure for protection of road and other allied work at different location under Augmentation work at Bidyadharpur W/S Scheme under North 24 Parganas District within the jurisdiction of N24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000197/2024-2025 | 189/NWSD-I | 31/01/2025 | 02/03/2025 | DAS TRADING | 9.86 | 0 | 0 | 0
Total | [13 empty] | 74.51 | 29.39 | 39.44