## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Repair, Renovation of Staff Quarter, Laboratory at Mangal Pandey WTP Premises, and Dariapur (Zone-VII-C) including civil works, supply of furniture, Sanitary arrangement & other allied works under office of The Executive Engineer, North 24 Pags. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000001/2023-2024 | 374/NWSD-I | 05/04/2023 | 05/05/2023 | PHOENIX INFRASTRUCTURE | 10.17 | 10.01 | 98.44 | 20
2 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, B (Telinipara) in Barrackpore-II Block of North 24 Parganas District. |  |  | ORD/001062/2023-2024 | 4033/ED | 17/10/2023 | 17/04/2024 | S.P. CONSTRUCTION | 34.15 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-II, B (Malikapur) in Barasat-I Block of North 24 Parganas District. |  |  | ORD/001058/2023-2024 | 4029/ED | 17/10/2023 | 17/04/2024 | A.G. ENTERPRISE | 55.55 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, B (Tapanpur) in Amdanga Block of North 24 Parganas District. |  |  | ORD/001061/2023-2024 | 4032/ED | 17/10/2023 | 17/04/2024 | ALPHA ENTERPRISE | 58.67 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Preparation of Augmentation DPR of Intake, Rising Main, WTP, Boosting Station of Surface Water Based Water Supply Project under North 24 Parganas Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) |  | ORD/000079/2022-2023 | 1079/NWSD-I | 29/09/2022 | 29/10/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 19.96 | 19.96 | 100 | 1
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Renovation of Administrative Building , Out House, Chemical House, Laboratory at Water Treatment Plant and 3 (Three) Nos. units of Boosting Station-I at Madhabpur by supplying Furnitures, Air Condition Machines and other allied works under Office of the Executive Engineer, NWSD-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER 2 | ORD/000139/2022-2023 | 352/NWSD-I | 27/03/2023 | 26/05/2023 | KINGS AND CO. | 133.48 | 123.98 | 92.88 | 100
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Repairing of damaged boundary wall at Mangal Pandey Water Treatment Plant site and other ancilary works under North 24 Pgs. Water Supply Division-I, P.H.E.Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000134/2023-2024 | 1391/NWSD-I | 05/09/2023 | 04/11/2023 | CONCORD ENGINEERING | 14.04 | 13.73 | 97.77 | 100
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 490/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 2047.44 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Feasibility study to select a suitable location for Water Intake (2.5 MGD) Jetty - Augmentation of Intake WTP & Rising Main for Surface Water Based Piped Water Supply Scheme of Mangal Pandey Water Treatment Plant for Arsenic Affected areas of North 24 Parganas under North 24 Pgs. W/S Division-I, P.H.E. Dte., Govt. of West Bengal. |  |  | BILL/00259/2023-2024 | 263/PFMS/23-24 | 03/10/2023 | 03/10/2023 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 53.67 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, Installation & Commissioning of 38 Nos of CCTV Camera for Indoor/Outdoor Purpose at Different area of Mangal Pandey Water Treatment Plant under North 24 Pgs. Water Supply Division-I, PHE. Dte.(2nd Call) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 2 | ORD/000021/2022-2023 | 550/NWSD-I | 29/04/2022 | 28/06/2022 | KIS MANAGEMENT PRIVATE LIMITED | 18.53 | 0.82 | 4.43 | 100
11 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-I (Surjapur) in Barrackpore-II & Barasat-I Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001055/2023-2024 | 4027/ED | 17/10/2023 | 17/04/2024 | WEST BENGAL ENGINEERING CO. | 30.05 | 0 | 0 | 10
12 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VI, A (Beraberia) in Amdanga & Barasat-I Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001056/2023-2024 | 4028/ED | 17/10/2023 | 17/04/2024 | WEST BENGAL ENGINEERING CO. | 33.17 | 0 | 0 | 10
13 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, A (Kharu) in Amdanga Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001054/2023-2024 | 4026/ED | 17/10/2023 | 16/01/2026 | ORIENTAL ENGINEERING CO. | 29.74 | 0 | 0 | 5
14 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-I, A-II (Chak Kanthalia) in Barrackpore-II Block of North 24 Parganas District. |  |  | ORD/001428/2023-2024 | 4889/ED | 27/12/2023 | 27/06/2024 | BENGAL CONSTRUCTION | 59.48 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Restoration Work by providing sand filling and G.S.B., W.M.M. & B.M. in damage Bituminous Road portion at different location in connection with the laying of rising main within the command area of Malikapur (Zone-IIB) W/S scheme due to cutting of existing black top road by open trench method for JJM/FHTC Project under North 24PGS Water Supply Divn.-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000023/2024-2025 | 1406/NWSD-I | 12/09/2024 | 12/10/2024 | BASHUDEV DUTTA | 59.38 | 0 | 0 | 100
16 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation Bill for New Service Connection at Kharu OHE Site |  |  | BILL/06153/2023-2024 | 785 | 20/02/2024 | 20/02/2024 | WBSEDCL | 1.41 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation for Sarberia OHR site Application no: 1007488840 SM 15816 |  |  | BILL/06219/2023-2024 | 852 | 07/03/2024 | 07/03/2024 | WBSEDCL | 2.05 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Tentulia Existing OHR site quotation received for Load Enhancement Application No. 1007958975 Consumer Id 153161466 SM Code : 15816 |  |  | BILL/02121/2024-2025 | 562 | 11/11/2024 | 11/11/2024 | WBSEDCL | 0.35 | 0 | 0 | 0
19 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation Bill for New Service Connection at Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Division-I, PHE Dte. |  |  | BILL/04594/2023-2024 | 592 | 29/12/2023 | 29/12/2023 | WBSEDCL | 1.08 | 0 | 0 | 0
20 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation Bill for New Service Connection at Beraberia OHR Site |  |  | BILL/06154/2023-2024 | 786 | 21/02/2024 | 21/02/2024 | WBSEDCL | 0.97 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation for New Service Connection at Khilkapur OHR site SM Code: 15816 |  |  | BILL/02609/2024-2025 | 634 | 18/12/2024 | 18/12/2024 | WBSEDCL | 6.96 | 0 | 0 | 0
22 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation Bill for New Service Connection at Berunanpukuria W/S. Sch. |  |  | BILL/04650/2023-2024 | 620 | 08/01/2024 | 08/01/2024 | WBSEDCL | 1.21 | 0 | 0 | 0
23 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 |  |  | BILL/06533/2023-2024 | 906 | 21/03/2024 | 21/03/2024 | WBSEDCL | 1.72 | 0 | 0 | 0
24 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supplimentory Quotation for Load enhancement of Surjapur OHR site for Mangal Pandey Augmentation SM Code: 15816 |  |  | BILL/06534/2023-2024 | 907 | 21/03/2024 | 21/03/2024 | WBSEDCL | 2.82 | 0 | 0 | 0
25 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supplimentory Quotation for Load enhancement of Telenipara OHR site for Mangal Pandey Augmentation SM Code: 15816 |  |  | BILL/06532/2023-2024 | 905 | 21/03/2024 | 21/03/2024 | WBSEDCL | 7.17 | 0 | 0 | 0
26 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Aug of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas at Kharki OHR site.[SM/15816] |  |  | BILL/01824/2024-2025 | 444 | 05/09/2024 | 05/09/2024 | WBSEDCL | 0.46 | 0 | 0 | 0
27 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Surjapur OHR Site Customer ID: 152146528 SM 15816 |  |  | BILL/06501/2023-2024 | 903 | 19/03/2024 | 19/03/2024 | WBSEDCL | 1.12 | 0 | 0 | 0
28 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 45.4 MLD) for Surface water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc. approach road & road restoration etc. for 21 Nos. distribution zone for Arsenic affected areas of North 24 Parganas District (Mangal pandey WTP) under North 24 Parganas Water Supply Division-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I,ASSISTANT ENGINEER (HQ-I),ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1,JUNIOR ENGINEER 2 | ORD/000118/2023-2024 | 1424/NWSD-I | 08/09/2023 | 08/09/2024 | RMN-SREE SUBHA JOINT VENTURE | 21400 | 59.51 | 0.28 | 2
29 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Augmentation of Centrifugal Pumping Machinery at Boosting Station - I along with disinfection arrangement at different zones under Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | Assistant Engineer 1 | Junior Engineer3 | ORD/001050/2023-2024 | 4022/ED | 17/10/2023 | 01/06/2025 | ORIENTAL ENGINEERING CO. | 323.41 | 115.82 | 35.81 | 5
30 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery to be installed at Zone-VII, C (Dariapur) for Augmentation of Zone-VIII, A/B/C in Amdanga Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001060/2023-2024 | 4031/ED | 17/10/2023 | 04/11/2025 | M/S P.P. ELECTRICALS | 109.28 | 0 | 0 | 20
31 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Renovation of High Lift Pumping Machinery, MCC panel, Sub-station equipments along with SCADA system at Water Treatment Plant of Mangal Pandey Surface based Water Supply Scheme in the District of North 24-Parganas. | Assistant Engineer 1 | Junior Engineer3 | ORD/001048/2023-2024 | 4020/ED | 17/10/2023 | 18/04/2025 | B.T. PROJECT PVT. LTD. | 392.78 | 252.41 | 64.26 | 5
32 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Providing Electro Mechanical equipments for Augmentation of Intake of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001049/2023-2024 | 4021/ED | 17/10/2023 | 16/01/2026 | ORIENTAL ENGINEERING CO. | 143.79 | 0 | 0 | 0
33 | NORTH 24 PARGANAS |  | Electrical | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Supply, delivery, installation & Commissioning of Electro Mechanical machinery under Augmentation of Surface Water Based Piped Water Supply Scheme for Zone-VII, B (Rautara) in Amdanga Block of North 24 Parganas District. | Assistant Engineer 1 | Junior Engineer3 | ORD/001059/2023-2024 | 4030/ED | 17/10/2023 | 04/01/2026 | DEY ENTERPRISE | 57.7 | 0 | 0 | 25
34 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Intake, WTP, Rising Main & Booster Station-I of Surface Water Based Piped Water Supply Scheme for Mangal Pandey under North 24 Parganas in North Barrackpore Municipality of North 24 Parganas District under North 24 Parganas Water Supply Di | SM/15816 | Augmentation | Road restoration along flank portion of bituminous road of PWD/ PMGSY/ Zilla Parisad/ Panchayet road due to laying of pipeline and reallocation Rising Main under Augmentation work at Telinipara (Zone-IB) W/S Scheme in Barrackpore-I Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (HQ-II) | JUNIOR ENGINEER (CIVIL) | ORD/000198/2024-2025 | 188/NWSD-I | 31/01/2025 | 17/03/2025 | DAS TRADING | 22.85 | 0 | 0 | 0
Total | [13 empty] | 25134.64 | 596.24 | 2.37