## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-III (Raypur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000060/2022-2023 | 228/NWSD-I | 28/02/2023 | 14/03/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.92 | 3.91 | 99.72 | 0
2 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 466/NWSD-I | 26/04/2023 |  | Resource Division | 151.42 | 0 | 0 | 0
3 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 1259/NWSD-I | 21/08/2023 |  | Resource Division | 23.65 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04761/2023-2024 | BP-298-23-24 | 28/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | null
5 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/04761/2023-2024 | BP-298-23-24 | 28/02/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.57 | 0 | 0 | null
6 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Additional quotation for New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) |  |  | BILL/05271/2023-2024 | BP-346-23-24 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.07 | 0 | 0 | null
7 | NORTH 24 PARAGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Additional quotation for New service connection at P.H.No- I of Raypur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N) |  |  | BILL/05271/2023-2024 | BP-346-23-24 | 15/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.07 | 0 | 0 | null
8 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000076/2023-2024 | 884/NWSD-I | 12/07/2023 | 06/07/2024 | S & P ENTERPRISE | 774.61 | 106.26 | 13.72 | 40
9 | NORTH 24 PARAGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Shifting of PCC Pole at Raypur OHR Site |  |  | BILL/00103/2024-2025 | 131/PFMS/24-25 | 30/07/2024 |  | WBSEDCL | 0.12 | 0 | 0 | null
11 | NORTH 24 PARAGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-III (Raypur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15819 | Augmentation | Shifting of PCC Pole at Raypur OHR Site |  |  | BILL/00103/2024-2025 | 131/PFMS/24-25 | 30/07/2024 |  | WBSEDCL | 0.12 | 0 | 0 | null
Total | [13 empty] | 22300.88 | 110.17 | 0.49