## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-V(Matikumra) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000063/2022-2023 | 257/NWSD-I | 10/03/2023 | 24/03/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.55 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 465/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 108.47 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 943/NWSD-I | 18/07/2023 | 18/07/2023 | Resource Division | 137.22 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2023-2024 | 1104/NWSD-I | 01/08/2023 | 01/08/2023 | Resource Division | 28.75 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Order for the work of " Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone- V (Matikumra) in Deganga Block of North 24 Parganas (s) District under North 24 Pgs W/S Div-I, PHE Dte". | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL),JUNIOR ENGINEER 1 | ORD/000050/2023-2024 | 678/NWSD-I | 01/06/2023 | 01/10/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 788.45 | 0 | 0 | 75
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | New service connection at OHR Site , Zone-V of Matikumra water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). |  |  | BILL/05033/2023-2024 | BP-342-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.53 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-V (Matikumra) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15820 | Augmentation | Laying of pipe line & special measure for protection of road and other allied works at different location under Augmentation work at Matikumra W/S. Scheme in Deganga Block under North 24Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000076/2024-2025 | 23/NWSD-I | 06/01/2025 | 21/01/2025 | RAJ ENTERPRISE | 4.94 | 0 | 0 | 0
Total | [13 empty] | 22414.67 | 0 | 0