## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000049/2023-2024 | 694/NWSD-I | 05/06/2023 | 05/06/2024 | M/S. TARAK CHANDRA PAUL | 751.17 | 519.96 | 69.22 | 85
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Detail route survey, design of distribution network and preparation of estimate drawing & DPR for providing FHTC in the scheme of Zone-II (Uttar Kalsur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000059/2022-2023 | 210/NWSD-I | 23/02/2023 | 09/03/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.36 | 4.36 | 99.91 | 0
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000008/2023-2024 | 467/NWSD-I | 26/04/2023 | 26/04/2023 | Resource Division | 219.63 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1103/NWSD-I | 01/08/2023 | 01/08/2023 | Resource Division | 30.14 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 944/NWSD-I | 18/07/2023 | 18/07/2023 | Resource Division | 249.77 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-II (Uttar Kalsur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/15822 | Augmentation | New service connection at OHR site of Uttar Kalsur water supply scheme under EMSD-I ,PHE Dte. In 24Pgs(N). Type : |  |  | BILL/05017/2023-2024 | BP-341-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.36 | 0 | 0 | 0
Total | [13 empty] | 22598.19 | 524.32 | 2.32