## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-XVI (Kalijug Biswanathpur) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000073/2023-2024 | 894/NWSD-I | 12/07/2023 | 26/07/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.79 | 3.78 | 99.64 | 100
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1371/NWSD-I | 04/09/2023 | 04/09/2023 | Resource Division | 129.72 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000026/2024-2025 | 1432/NWSD-I | 18/09/2024 | 02/10/2024 | S M TRADERS | 2.17 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Development of approach Road at Head Work Site Kalijug Biswanathpur (Zone-XVI) W/S Scheme in Deganga Block under North 24 Pgs W/S Division-I, PHE. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000006/2024-2025 | 904/NWSD-I | 19/06/2024 | 03/07/2024 | RAKESH ENTERPRISE | 13.36 | 13.29 | 99.42 | 100
5 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 230/NWSD-I | 06/02/2024 | 06/02/2024 | Resource Division | 21.71 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | New service connection at Kalijug Biswanathpur P.H.No- I Zone- XVI water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/05026/2023-2024 | BP-333-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.73 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 29.23 | 0.14 | 11
8 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Providing FHTC, Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone- XVI (KALIJUG BISWANATHPUR) in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000086/2023-2024 | 1009/NWSD-I | 25/07/2023 | 31/07/2026 | H. I. ENTERPRISE | 762.31 | 501.32 | 65.76 | 82
9 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-XVI (Kalijug Biswanathpur) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18260 | Augmentation | Laying of pipeline & other allied work at different location under Augmentation work at Kalijug-Biswanathpur W/S. Scheme in Deganga Block under North 24 Pgs W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER (CIVIL) | ORD/000018/2025-2026 | 725/NWSD-I | 19/05/2025 | 15/12/2025 | H. I. ENTERPRISE | 76.14 | 0 | 0 | 65
Total | [13 empty] | 22353.7 | 547.62 | 2.45