## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme of Zone-VIII (Chyangdana) under North 24 Pgs. W/S Division-I, P.H.E. Dte. | ASSISTANT ENGINEER (CIVIL), NWSSD-I | JUNIOR ENGINEER 1 | ORD/000070/2023-2024 | 891/NWSD-I | 12/07/2023 | 26/07/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.76 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1835/NWSD-I | 10/11/2023 | 10/11/2023 | Resource Division | 55.11 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Supply and installation of Sign Board (900mm X 600mm) determination of Land i.e." This land belongs to PHE. Dte. Govt. of West Bengal" under Surface Water based Pipe Water supply Scheme under North 24 Pgs. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000026/2024-2025 | 1432/NWSD-I | 18/09/2024 | 02/10/2024 | S M TRADERS | 2.17 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 39/NWSD-I | 05/01/2024 | 05/01/2024 | Resource Division | 16.58 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Eastern Mechanical | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | New service connection at Chyangdana P.H.No-I Zone- VIII water supply scheme under EMSD-I ,PHE Dte .in 24Pgs(N). |  |  | BILL/05030/2023-2024 | BP-337-23-24 | 11/03/2024 | 11/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.4 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Central Drilling | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
7 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Augmentation of Surface Water Based Piped Water Supply Scheme for Arsenic Affected areas of Zone-VIII (Chyangdana) in Deganga Block of North 24 Parganas District Under North 24 Parganas W/S Division-I, PHE Dte. | SM/18262 | Augmentation | Laying of Distribution System including specials, valves & pipe carrying structure, Proposed Rising Main System, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, 10 mm gun metal ferrule, saddle piece etc. all complete, Construction of 500 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation (600 mm dia, 22 mtrs. deep and one pile cap adjoning 3 nos of piles) , pipe connection and cost of pipes, specials., Soil Investigation for the work of construction of OHR with staging height 20 mtr, Construction Of Pump House (4.88m X 3.66m) Including Sanitary Arrangement, Boundary Wall, Service Road for 60 M length, Improvement Of Land for Augmentation of Surface Water Based Piped Water Supply Scheme of Arsenic Affected areas of Zone-VIII CHYANGDANA in Deganga Block of North 24 Pargana(s) District under N 24 Pgs W/S Div-I, PHE Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000173/2023-2024 | 1675/NWSD-I | 30/10/2023 | 01/04/2026 | SINGHA ROY AND CO | 676.75 | 0 | 0 | 10
Total | [13 empty] | 22099.53 | 0 | 0