## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. | SM/19088 | Support-WQMSP | Supply of chemical & Consumable reagents and other laboratory related items at Mangal Pandey WTP water Testing Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000003/2024-2025 | 1175/NWSD-I | 05/08/2024 | 04/09/2024 | M/S. LAXMI ENTERPRISE. | 0.25 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. | SM/19088 | Support-WQMSP | Engagement of Laboratory personnel for Day to Day Water testing at Mangal Pandey WTP Water Testing Laboratory in the status of District Laboratory under North 24 Pgs. W/S. Division-I, PHE. Dte. For the period of 01 (One) year. i.e. 366 Days. (01.09.2023 to 31.08.2024) | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000129/2023-2024 | 1324/NWSD-I | 29/08/2023 | 29/08/2024 | M/S. PHOENIX INFRASTRUCTURE | 26.99 | 0 | 0 | 66
3 | NORTH 24 PARGANAS |  | North 24 Pgs W/S Division I | Operational charges of Mangal Pandey WTP Water Testing Laboratory related to Water Quality Monitoring & Surveillance including procurement of Chemicals, Consumables, Glassware pertaining to NABL & BIS scopes. | SM/19088 | Support-WQMSP | Supply of chemical & Consumable reagents and other laboratory related items at Mangal Pandey WTP water Testing Laboratory under North 24 PGS. Water Supply Division-I, PHE. Dte. | ASSISTANT ENGINEER (HQ-I) | JUNIOR ENGINEER (CIVIL) | ORD/000002/2024-2025 | 1176/NWSD-I | 05/08/2024 | 04/09/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 3.06 | 0 | 0 | 100
Total | [13 empty] | 30.29 | 0 | 0