## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the South 24 Pgs District. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 1980/RS | 25/07/2024 | 25/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 103.2 | 0 | 0 | 50
2 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the South 24 Pgs District. | Assistant Engineer | Junior Engineer | ORD/000059/2024-2025 | 1980/RS | 25/07/2024 | 25/01/2025 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 103.2 | 0 | 0 | 50
3 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 3202/RS | 31/12/2024 | 31/03/2025 | HALDAH EASTERN DEVELOPMENT SOCIETY | 116.68 | 0 | 0 | 99
4 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000217/2024-2025 | 3202/RS | 31/12/2024 | 31/03/2025 | HALDAH EASTERN DEVELOPMENT SOCIETY | 116.68 | 0 | 0 | 99
5 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000323/2023-2024 | 712/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 403.7 | 0 | 0 | 50
6 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM in the districts of the North 24 Pgs . | Assistant Engineer | Junior Engineer | ORD/000323/2023-2024 | 712/RS | 01/03/2024 | 01/01/2025 | IMAGIN | 403.7 | 0 | 0 | 50
7 | NORTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000321/2023-2024 | 734/RS | 04/03/2024 | 04/01/2025 | HALDAH EASTERN DEVELOPMENT SOCIETY | 355.2 | 0 | 0 | 50
8 | SOUTH 24 PARGANAS |  | Resource | Engagement of Implementation Support Agencies (ISAs) for implementation of community mobilization & capacity building activities at South 24 Parganas & North 24 Parganas districts Under Jal Jeevan Mission (JJM) Support Activities | SM/19235 |  | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the South24 Parganas | Assistant Engineer | Junior Engineer | ORD/000321/2023-2024 | 734/RS | 04/03/2024 | 04/01/2025 | HALDAH EASTERN DEVELOPMENT SOCIETY | 355.2 | 0 | 0 | 50
Total | [13 empty] | 1957.57 | 0 | 0