## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 327/RS | 10/02/2025 | 10/07/2025 | HORIZEN | 8.31 | 0 | 0 | 68
2 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Design, Development and Maintenance of a Monitoring System for the Activities executed by the Implementation Support Agencies (ISA) for establishing a Decision Support System | Assistant Engineer | Junior Engineer | ORD/000333/2024-2025 | 327/RS | 10/02/2025 | 10/07/2025 | HORIZEN | 8.31 | 0 | 0 | 68
3 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
4 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Scrutinization and verification of pump house data under WBSEDCL through continuous field visits and consultation with the Mechanical/Electrical wing of the PHE Department, including creation of an online monitoring system to ensure accurate and seamless recording of daily activities at pump houses regarding functioning of pumps & motors, chlorination arrangements etc. to facilitate continuous energy audits and future verification of WBSEDCL data | Assistant Engineer | Junior Engineer | ORD/000102/2025-2026 | 2033/RS | 04/09/2025 | 04/09/2026 | HORIZEN | 86.02 | 0 | 0 | 7
5 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module. | Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 932/RS | 29/04/2025 | 29/06/2025 | HORIZEN | 17.33 | 0 | 0 | 50
6 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Enhancement of the Jalmitra application to facilitate comprehensive functionality assessment of household tap connections, Maintenance, Upgradation & Modification of the Android and Web Module. | Assistant Engineer | Junior Engineer | ORD/000039/2025-2026 | 932/RS | 29/04/2025 | 29/06/2025 | HORIZEN | 17.33 | 0 | 0 | 50
7 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000040/2025-2026 | 798/RS | 08/04/2025 | 08/05/2025 | HORIZEN | 4.33 | 0 | 0 | 60
8 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Restructuring, redesigning of Map Domain, Upload & hosting of high-quality maps in vector & raster format; with provision of user-friendly customized query as well as download option in various formats with respect to Piped Water Supply Schemes | Assistant Engineer | Junior Engineer | ORD/000040/2025-2026 | 798/RS | 08/04/2025 | 08/05/2025 | HORIZEN | 4.33 | 0 | 0 | 60
9 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
10 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Collection, Scanning and Digitization of printed distribution drawings from divisions/subdivisions of the PHE Directorate into Geo-referenced CAD files and uploading them in the PHED "Scheme Drawing & Litholog" Module along with development of a GIS tool facilitating a user-friendly, integrated data entry panel designed for capturing essential attributes such as material, diameter, and connection points to convert a design drawing into an in-built drawing under Support Activities of Jal Jeevan Mission. | Assistant Engineer | Junior Engineer | ORD/000018/2025-2026 | 1026/RS | 14/05/2025 | 11/09/2025 | HORIZEN | 78.73 | 0 | 0 | 10
11 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
12 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Digitization of the transmission, distribution system, and all assets of piped water supply schemes, converting them to Keyhole Markup Language (.kml) files for uploading in the PM Gati Shakti Portal, along with digitization, preparation, and upload of lithologic drawings received from divisions/sub-divisions of the PHED Directorate under Support Activities of Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000008/2025-2026 | 929/RS | 29/04/2025 | 26/10/2025 | HORIZEN | 80.97 | 0 | 0 | 56
13 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
14 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Development and Deployment of a Technology-Enabled, Multi-Channel Grievance Redressal System to Enhance Transparency, Service Accountability, and Real-Time Citizen Engagement in Rural Water Supply Management for Asset Management and Maintenance under Jal Jeevan Mission | Assistant Engineer | Junior Engineer | ORD/000121/2025-2026 | 2184/RS | 23/09/2025 | 23/09/2026 | HORIZEN | 96.41 | 0 | 0 | 60
15 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
16 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Extraction, harmonization, and spatial integration of pipeline infrastructure data across all relevant Piped Water Supply Schemes to enable geospatial visualization, performance monitoring, functionality assessment, and data-driven strategic planning for Asset management and subsequent Operation & Maintenance procedure within the Jal Jeevan Mission implementation framework under PHED WB. | Assistant Engineer | Junior Engineer | ORD/000156/2025-2026 | 2617/RS | 10/12/2025 | 08/06/2026 | HORIZEN | 224.32 | 0 | 0 | 40
17 | NORTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Engagement of 2(Two) nos. peon on monthly contractual basis for the office of the Executive Engineer, SID, PHE Dte., for a period of 03(Three) months from 01/06/2025 to 31/08/2025. |  |  | ORD/000247/2025-2026 | 1136/Rs | 26/05/2025 | 26/05/2025 | UNIQUE ALLIED SECURITY SERVICE | 0.93 | 0 | 0 | 100
18 | SOUTH 24 PARGANAS |  | Resource | Acquisition of Field Level Data of Headwork Site and Distribution System of different Piped Water Supply Schemes and Updation of the Same in the WB-PHED Web Module for the Districts North 24 Parganas and South 24 Parganas (Phase-I) | SM/19254 | Support-MIS | Engagement of 2(Two) nos. peon on monthly contractual basis for the office of the Executive Engineer, SID, PHE Dte., for a period of 03(Three) months from 01/06/2025 to 31/08/2025. |  |  | ORD/000247/2025-2026 | 1136/Rs | 26/05/2025 | 26/05/2025 | UNIQUE ALLIED SECURITY SERVICE | 0.93 | 0 | 0 | 100
Total | [13 empty] | 1194.72 | 0 | 0