## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Implementation of Affordable IoT- System at Baunia Abad Water Supply Scheme under Sandeshkhali- I Block of 24 Pgs.(N) District in West Bengal. | SM/17096 | IOT | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. |  |  | ORD/002104/2022-2023 | 3387 / EMD | 09/09/2022 | 09/10/2022 | GOENKA ENTERPRISE | 11.36 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Eastern Mechanical | Implementation of Affordable IoT- System at Baunia Abad Water Supply Scheme under Sandeshkhali- I Block of 24 Pgs.(N) District in West Bengal. | SM/17096 | IOT | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II (replacement) under Baunia Abad W/S Scheme District of North 24 Pgs. |  |  | ORD/002101/2022-2023 | 3388 / EMD | 09/09/2022 | 09/10/2022 | POLYCON ENGINEERS | 11.36 | 0 | 0 | 0
Total | [13 empty] | 22.72 | 0 | 0