## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Eastern Mechanical | Implementation of Affordable IoT- System at Dwarir Jangle Water Supply Scheme under Sandeshkhali- II Block of 24 Pgs.(N) District in West Bengal. | SM/17112 | IOT | Acceptance of Implementation of Affordable loT-Enable Water Service Delivery Measurement and Monitoring Sensing System in Rural PWSS under Jal Jeevan Mission in the district of North 24 Parganas and Nadia in West Bengal under Eastern Mechanical Division, PHED. (i) Your Memo. no. WTL/T3/PHE/24-25/050-11 dt.30.07.2024 (ii) Order No. 2253/PHE-1 13018/9/2024-SCHM CELL-Dept. of PHE of the Special Sect. to the GOWB (iii) Memo. No. 12079/Works/Misc/000012/2023 dt. 30.08.2024 of the CE(M/E), SZ, PHE Dte. (iv) Memo. No. 468/1-3/MC-III dt. 30.08.2024 of the SE/MC-III/PHED. | Assistant Engineer | Junior Engineer,Junior Engineer (Mechanical) | ORD/001473/2024-2025 | 2205/EMD | 04/09/2024 | 04/02/2025 | WEBEL TECHNOLOGY LTD. | 5750.24 | 0 | 0 | 30
Total | [13 empty] | 5750.24 | 0 | 0