## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000043/2020-2021 | 1886/B.Ar.D. | 18/12/2020 | 18/03/2021 | UMA CONSTRUCTION | 39.19 | 29.46 | 75.17 | 1
2 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Protection of UPVC Pipeline ( approx 50 m.) near Pond of Ajarul Gazi, Safikul Islam and near Ramkrishna Brick Field under Command area of Magurati Srirampur W/S Scheme of Baduria Block in Connection of Retrofiting work for providing FHTC under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000152/2020-2021 | 300/B.Ar.D | 03/02/2021 | 23/02/2021 | NEW BRIGHT CONSTRUCTION | 3.99 | 0 | 0 | 1
3 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Surrender and transfer of unspent JJM fund. |  |  | VCH/000759/2021-2022 | 518 | 11/02/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 259.1 | 0 | 0 | 0
4 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Surrender and transfer of unspent JJM fund. |  |  | VCH/000759/2021-2022 | 518 | 11/02/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 259.1 | 0 | 0 | 0
5 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Magurati Srirampur W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000187/2021-2022 | 282/B.Ar.D | 22/02/2022 | 14/03/2022 | NIKHIL SAMADDAR | 4.62 | 0 | 0 | 1
6 | NORTH 24 PARAGANAS |  | Barasat Arsenic Division | Rejuvination of Magurati Srirampur water supply scheme under Baduria Block for providing Functional House Tap Conection | SM/07021 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Srikrishna Sarkar at purbapara under Magurati Srirampur W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000291/2021-2022 | 560/B.Ar.D | 23/03/2022 | 07/04/2022 | A 8T CONSTRUCTION | 4.11 | 4.11 | 99.92 | 100
Total | [13 empty] | 570.1 | 33.56 | 5.89