## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07022 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Ghola, Rajapura and Chalitabaria Mouzas of Hasnabad Block from Rajapura Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000039/2020-2021 | 1881/B.Ar.D. | 18/12/2020 | 18/03/2021 | UTPAL CONSTRUCTION AND CO | 96.59 | 61.47 | 63.64 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Rajapura water supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07022 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000041/2020-2021 | 1884/B.Ar.D. | 18/12/2020 | 18/03/2021 | UTPAL CONSTRUCTION AND CO | 83.3 | 100 | 120.04 | 1
Total | [13 empty] | 179.9 | 161.47 | 89.75