## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07024 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Muragachha, Harikati and Krishnapara Mouzas of Hasnabad Block from Krishnapara Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000041/2020-2021 | 1884/B.Ar.D. | 18/12/2020 | 18/03/2021 | UTPAL CONSTRUCTION AND CO | 83.3 | 132.04 | 158.5 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Rejuvenation of Krishnapara Water Supply scheme under Hasnabad Block for providing Functional House Tap Connection | SM/07024 | Retrofitting | Route survey, Distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Krishnapara & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000030/2021-2022 | 1444/B.Ar.D | 31/08/2021 | 15/09/2021 | RISHAN ENGINEERING CONSULTANCY | 2.49 | 2.49 | 100 | 1
Total | [13 empty] | 85.8 | 134.53 | 156.8