## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection | SM/07027 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Khorda, Jalsira and Konanagar Mouzas of Hasnabad Block from Konanagar Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. ( Phase-I ). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000035/2020-2021 | 1880/B.Ar.D. | 18/12/2020 | 18/03/2021 | M/S ROY CHOWDHURY & CO. | 82.2 | 146.38 | 178.07 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection | SM/07027 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Konanagar , Rajapura & its adjoining mouza Water Supply Scheme in Hasnabad Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000029/2021-2022 | 1443/B.Ar.D | 31/08/2021 | 15/09/2021 | SIRCON ENGINEERING SERVICES | 4.74 | 4.39 | 92.56 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Konanagar water supply scheme under Hasnabad Block for providing Functional House Tap Conection | SM/07027 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Magurati Srirampur Mouza of Baduria Block from Magurati Srirampur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000043/2020-2021 | 1886/B.Ar.D. | 18/12/2020 | 18/03/2021 | UMA CONSTRUCTION | 39.19 | 14.23 | 36.31 | 1
Total | [13 empty] | 126.13 | 164.99 | 130.82