## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/07706 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Atapur Water Supply Scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000026/2021-2022 | 1440/B.Ar.D | 31/08/2021 | 15/09/2021 | RISHAN ENGINEERING CONSULTANCY | 2.41 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/07706 | Retrofitting | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Atapur, Dwarir Jungle & Jeliakhali Paschim Khanda Ground Water Supply Scheme under Sandeshkhali-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000223/2021-2022 | 341/B.Ar.D | 28/02/2022 | 15/03/2022 | M/S.KRISHNA MONDAL | 3.97 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/07706 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Atapur Mouza of Sandeshkhali-II Block from Atapur Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000127/2020-2021 | 136/B.Ar.D. | 21/01/2021 | 21/04/2021 | M/S NIRMAN CONSTRUCTION | 60.13 | 35.13 | 58.43 | 80
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Atapur water supply scheme under sandeshkhali- II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/07706 | Retrofitting | Laying of UPVC Pipe Line from pump house no 1 towards Duchnekhali bazar for Functional House Hold Tap Connection under command area of Atapur water supply scheme of Sandeshkhali - II Block under JJM Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, Barasat Arsenic Sub-Division,Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000189/2022-2023 | 470/B.Ar.D. | 27/02/2023 | 29/03/2023 | P. & S. ASSOCIATES | 11.83 | 0 | 0 | 0
Total | [13 empty] | 78.34 | 35.13 | 44.85