## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Puturia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000039/2021-2022 | 1563/B.Ar.D. | 15/09/2021 | 30/09/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.19 | 6.19 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Jiyawal at Bokanda Majher Para under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000265/2021-2022 | 475/B.Ar.D | 16/03/2022 | 31/03/2022 | CHAKRABORTY SUPPLIERS & CONSTRUCTION | 4.68 | 4.67 | 99.71 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Simulgachhi, Bonkanda and Baidyapur Mouzas of Barasat- II Block from Puturia Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000123/2020-2021 | 127/B.Ar.D. | 20/01/2021 | 20/04/2021 | BANI ENGINEERING CO | 94.63 | 80.52 | 85.09 | 100
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near Najrul house and Hafijul house at Simulgachi under Puturia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000275/2021-2022 | 481/B.Ar.D | 16/03/2022 | 31/03/2022 | M/S.KRISHNA MONDAL | 4.79 | 4.79 | 99.99 | 70
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07707 | Retrofitting | Repair & Renovation of Iron Elimination Plant of 161 M3 including Media Change of Puturia Water Supply Scheme under Barasat- II Block Under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-I, Barasat Arsenic Division | Junior Engineer | ORD/000027/2023-2024 | 1165/B.Ar.D. | 16/05/2023 | 15/06/2023 | GHOSH CONSTRUCTION | 8.71 | 8.32 | 95.52 | 100
Total | [13 empty] | 119 | 104.49 | 87.81