## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bahira & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000060/2021-2022 | 1692/B.Ar.D | 30/09/2021 | 15/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.62 | 4.62 | 99.99 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Fanindra Nath Karmakar and Kena Ghosh at Baghyabantapur under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000266/2021-2022 | 476/B.Ar.D | 16/03/2022 | 31/03/2022 | SAHA ENTERPRISE | 4.73 | 4.72 | 99.94 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Aribulla at Pagdha Dakshinpara under Bahira W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000274/2021-2022 | 480/B.Ar.D | 16/03/2022 | 31/03/2022 | DIPA CHHETRI | 4.59 | 4.59 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Chakaminpur, Pakdaha and Balipur Mouzas of Barasat- II Block from Bahira Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000126/2020-2021 | 135/B.Ar.D. | 21/01/2021 | 21/04/2021 | BANI ENGINEERING CO | 87.16 | 16.85 | 19.34 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07708 | Retrofitting | Laying of UPVC Pipe Line at damaged portion of distribution network near Dadpur Gabtala Market of Bahira water supply scheme at Barasat-II Block due to construction of culvert and Drain under Barasat Arsenic Division, PHE Dte. under 'JAL JIBAN MISSION' Programme. (SM/07708) (Sl No. 3) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000140/2022-2023 | 2088/B.Ar.D. | 28/10/2022 | 18/11/2022 | M/S DATTA ENTERPRISE | 4.93 | 4.92 | 99.86 | 1
Total | [13 empty] | 106.03 | 35.71 | 33.68