## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07709 | Retrofitting | Providing Functional School , Anganwadi and Health Center Tap Connection and allied works of Command area at Bagband-Saiberia Ground Water Supply Scheme under Barasat-II Block Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000180/2021-2022 | 267/B.Ar.D | 18/02/2022 | 10/03/2022 | A P POWER AND CONCRETE | 3.9 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07709 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Bagband-Sarberia, Kirttipur and Krishnamati Mouzas of Barasat- II Block from Bagband Saiberia Ground Water Supply Scheme Under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000124/2020-2021 | 128/B.Ar.D. | 20/01/2021 | 20/04/2021 | R. K. MANDAL & CO. | 85.38 | 70.76 | 82.89 | 100
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07709 | Retrofitting | Laying of HDPE Pipe Line in damaged portion of distribution network at Gobindapur under Bagband-Saiberia Water Supply Scheme under under Barasat Arsenic Division, PHE Dte. (SM/07709) (Sl No. 2) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000139/2022-2023 | 2087/B.Ar.D. | 28/10/2022 | 18/11/2022 | BALAJEE ENTERPRISES | 4.2 | 0 | 0 | 1
Total | [13 empty] | 93.48 | 70.76 | 75.7