## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07710 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Mahishgadi Mouza of Barasat- II Block from Mahishgadi Ground Water Supply Scheme Under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000125/2020-2021 | 134/B.Ar.D. | 21/01/2021 | 21/04/2021 | BANI ENGINEERING CO | 96.59 | 136.24 | 141.04 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07710 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Mahisgadi & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000063/2021-2022 | 1700/B.Ar.D | 30/09/2021 | 15/10/2021 | UMWELT ENGINEER PVT. LTD. | 2.95 | 2.95 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahishgadi & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07710 | Retrofitting | Laying of MS Pipe and allied work at Haroa Khal Crossing of Mahisgadi water supply Scheme and Boaring works related to FHTC works of Mahisgadi water supply Scheme at Barasat-II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000270/2021-2022 | 479/B.Ar.D | 16/03/2022 | 31/03/2022 | BALAJEE ENTERPRISES | 4.77 | 4.76 | 99.74 | 1
Total | [13 empty] | 104.31 | 143.95 | 137.99