## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Dakshindiara, Chak Khamarpur, Shrikati, Jagannathpur and Mahespur Mouzas of Baduria Block from Tildanga Ground Water Supply Scheme under " Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000217/2020-2021 | 562/B.Ar.D. | 26/02/2021 | 27/05/2021 | SANJUKTA ENGINEERS | 82.47 | 101.42 | 122.98 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Magurati Srirampur, Tildanga & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000031/2021-2022 | 1445/B.Ar.D | 31/08/2021 | 15/09/2021 | SIRCON ENGINEERING SERVICES | 4.06 | 4.06 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Asraf Ali at Srikati Sesher para under Tildanga W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000263/2021-2022 | 473/B.Ar.D | 16/03/2022 | 31/03/2022 | G. S. CONSTRUCTION & CO. | 4.45 | 4.44 | 99.91 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | Retrofitting | Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of Tildanga Water Supply Scheme under Baduria Block under Barasat Arsenic Division, PHE Dte. (SM/07712) (Sl No. 1) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000138/2022-2023 | 2086/B.Ar.D. | 28/10/2022 | 12/11/2022 | BALAJEE ENTERPRISES | 3.95 | 3.94 | 99.75 | 1
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Tildanga & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07712 | Retrofitting | Withdrawal and Relaying of 160 mm dia. HDPE rising main pipeline along with protection work and other allied works near 2nd Pump House under Tildanga W/S Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000029/2023-2024 | 1168/B.Ar.D. | 16/05/2023 | 15/06/2023 | M/S DATTA ENTERPRISE | 4.84 | 4.78 | 98.74 | 100
Total | [13 empty] | 99.76 | 118.63 | 118.92