## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Chowlpur, Ghoradaria and Mitpukuria Mouzas of Barasat- II Block from Chowlpur Ground Water Supply Scheme under "Jal swapna" programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000216/2020-2021 | 561/B.Ar.D. | 26/02/2021 | 27/05/2021 | SANJUKTA ENGINEERS | 77.59 | 107.62 | 138.71 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Chowlpur & its adjoining mouza water supply scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000061/2021-2022 | 1698/B.Ar.D | 30/09/2021 | 15/10/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.04 | 3.04 | 99.9 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Chowlpur W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000140/2021-2022 | 2217/B.Ar.D | 24/12/2021 | 23/01/2022 | CHOWDHURY CONSTRUCTION | 4.8 | 4.8 | 99.85 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling (approx. 50 mtr length) for protection of different dia UPVC/HDPE Pipeline near two ponds at Ghoradaria opposite Gour Biswas house and at Malrameswarpur Sardarhati opposite Pranab Sarkar house under Chowlpur W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000184/2021-2022 | 288/B.Ar.D | 23/02/2022 | 15/03/2022 | CHOWDHURY CONSTRUCTION | 4.8 | 4.26 | 88.71 | 1
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Chowlpur & its adj. mouzas water supply scheme for providing Functional House Tap Connection (Phase-I) | SM/07713 | Retrofitting | Renovation of Pathway and Painting of boundary wall and other allied works at Chowlpur Head Work Site under Chowlpur Water Supply scheme of Barasat ll Block under JAL SWAPNA Programme under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000278/2021-2022 | 484/B.Ar.D | 16/03/2022 | 31/03/2022 | MODERN CONSTRUCTIONS | 4.64 | 0 | 0 | 1
Total | [13 empty] | 94.87 | 119.71 | 126.18