## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) | SM/08176 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Paltadanga & its adjoining mouza water supply scheme in Barasat - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000064/2021-2022 | 1701/B.Ar.D | 30/09/2021 | 15/10/2021 | UMWELT ENGINEER PVT. LTD. | 4.7 | 4.7 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) | SM/08176 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Kismat sonatikari, Sonatikari, Dugdia and Bharparbara Malik Mouzas of Barasat II Block from Paltadanga & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000169/2020-2021 | 465/B.Ar.D. | 19/02/2021 | 20/05/2021 | BALAJEE ENTERPRISES | 60.68 | 118.18 | 194.76 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Paltadanga & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) | SM/08176 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Paltadanga W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000138/2021-2022 | 2218/B.Ar.D | 24/12/2021 | 23/01/2022 | KUNDU CONSTRUCTION CO. | 4.79 | 4.78 | 99.76 | 1
Total | [13 empty] | 70.17 | 127.66 | 181.93