## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | SM/08177 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Gobindapur, Madanpur Krishnapur and Andulia Mouzas of Barasat II Block from Bagband Saiberia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000170/2020-2021 | 466/B.Ar.D. | 19/02/2021 | 20/05/2021 | BALAJEE ENTERPRISES | 79.53 | 108.85 | 136.88 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | SM/08177 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Bagband Saiberia & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000038/2021-2022 | 1562/B.Ar.D. | 15/09/2021 | 30/09/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.94 | 6.94 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | SM/08177 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Bablu Ali at Saiberia Uttarpara and Mosharef Ali at Saiberia Moral Para under Bagband Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000264/2021-2022 | 474/B.Ar.D | 16/03/2022 | 31/03/2022 | WATERCOMP INDIA | 4.71 | 4.71 | 99.88 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bagband Saiberia & Its adjoining Mouzas water Supply Scheme under Barasat- II Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- II) . | SM/08177 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Ajibar Baidhya at Saiberia Baidhyapara and Akkaj Ali at saiberia Uttar para under Bagbandh Saiberia W/S Scheme at Barasat- II block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000292/2021-2022 | 561/B.Ar.D | 23/03/2022 | 07/04/2022 | KAKALI ENTERPRISE | 4.71 | 4.71 | 99.92 | 100
Total | [13 empty] | 95.89 | 125.21 | 130.57