## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08178 | Retrofitting | Providing Functional House Hold Connection and Allied workas at Bahira and BhagyantpurMouzas of Barasat II Block from Bahira & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000171/2020-2021 | 467/B.Ar.D. | 19/02/2021 | 20/05/2021 | M/S JHARNA ENTERPRISE | 80.88 | 160.1 | 197.95 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08178 | Retrofitting | Construction of pathway and allied works at the site of Bahira W/S Scheme under Jal Swapna Programme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000189/2021-2022 | 277/B.Ar.D | 21/02/2022 | 13/03/2022 | S. S. CONSULTANCY & CONSTRUCTION | 4.59 | 4.58 | 99.84 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08178 | Retrofitting | Repairing and Renovation of 02 (two) nos pump house and 01 (one) No I.E.P room, and allied works at the site of Bahira W/S Scheme at Barasat-II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000092/2021-2022 | 1829/B.Ar.D | 01/11/2021 | 01/12/2021 | S. S. CONSULTANCY & CONSTRUCTION | 4.79 | 4.79 | 99.93 | 70
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Bahira & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08178 | Retrofitting | Specials Repairing of Rising Main & Interconnection of 168.3 mm dia Ms pipe 250mm dia & 150 mm dia DI pipe at Bahira H/W Site under Bahira W/S Scheme at Barasat-II block under Barasat Arsenic Division, PHE Dte. under JAL SWAPNA Programme. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000220/2021-2022 | 339/B.Ar.D | 28/02/2022 | 15/03/2022 | BANI ENGINEERING CO | 4.6 | 0 | 0 | 0
Total | [13 empty] | 94.87 | 169.48 | 178.65