## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08179 | Retrofitting | Withdrawing and Laying of UPVC Pipe Line in damaged portion of distribution network and protection work of UPVC line at Puturia -Kharbil of Puturia Water Supply Scheme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000096/2021-2022 | 1833/B.Ar.D | 01/11/2021 | 01/12/2021 | M/S. BAKSHI ENTERPRISE | 4.78 | 4.73 | 98.93 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08179 | Retrofitting | Emergent protection of UPVC distribution pipe line near 2nd Pump House at PUTURIA W/S of Barasat II block under retrofitting of Puturia W/S for providing FHTC (Phase-I) under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000181/2021-2022 | 268/B.Ar.D | 18/02/2022 | 11/03/2022 | BAKSHI ENTERPRISE | 4.47 | 4.48 | 100.17 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08179 | Retrofitting | Providing Functional House Hold Connection and Allied workas at puturia and Tona Mouzas of Barasat II Block from Puturia & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000172/2020-2021 | 468/B.Ar.D. | 19/02/2021 | 20/05/2021 | SAKTI ENTERPRISE | 75.31 | 38.28 | 50.82 | 100
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Puturia & Its Adjoining Mouzas Water Supply Scheme for providing Functional House Tap Connection ( Phase- II) | SM/08179 | Retrofitting | Laying UPVC Pipeline for Providing Functional Household Tap Connection of Command area at Puturia Ground Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division PHE, Dte. (SM/08179) (Sl No. 4) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000141/2022-2023 | 2124/B.Ar.D. | 04/11/2022 | 19/11/2022 | SAKTI ENTERPRISE | 2.63 | 2.63 | 99.89 | 1
Total | [13 empty] | 87.19 | 50.11 | 57.47