## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08245 | Retrofitting | Route survey, distribution design & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jasaikhati Zone - I & its adjoining mouza Water Supply Scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000027/2021-2022 | 1441/B.Ar.D | 31/08/2021 | 15/09/2021 | SIRCON ENGINEERING SERVICES | 4.7 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08245 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Mulluk Chand at danga uttarpara and Sumon Mondal at uttar chowdhury para under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000276/2021-2022 | 482/B.Ar.D | 16/03/2022 | 31/03/2022 | TEN STAR ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.58 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08245 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at kankrasuti mouza of Baduria Block from Jashaikati Zone -I & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I). | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000002/2021-2022 | 1035/B.Ar.D. | 07/06/2021 | 05/09/2021 | UTPAL CONSTRUCTION AND CO | 96.04 | 0 | 0 | 100
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone I & Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas ( Phase- I) . | SM/08245 | Retrofitting | Bullah Pilling for protection of Pipeline ( Approx 60 m) near pond of Sumon Haldar at Jasaikathi (Z-I) W/S Scheme at Baduria Block under Jal Swapna Programme under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000150/2021-2022 | 2232/B.Ar.D | 28/12/2021 | 27/01/2022 | M/S DATTA ENTERPRISE | 4.45 | 0 | 0 | 100
Total | [13 empty] | 109.78 | 0 | 0