## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/08247 | Retrofitting | Route survey, Distribution designe & DPR preparation for Providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Rohanda & its adjoining mouza Water Supply Scheme in Barasat -II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000040/2021-2022 | 1564/B.Ar.D. | 15/09/2021 | 30/09/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 5.78 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Rohanda & Its adjoining Mouzas Water Supply Scheme under Barasat II Block for providing Functional House Tap Connection in North 24 Pargana District (Phase-I) | SM/08247 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Palitpara, Rohanda, Noapara, Banpol, Singhapra mouza's of Barasat - II Block from Rohanda & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-I) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000004/2021-2022 | 1037/B.Ar.D. | 07/06/2021 | 05/09/2021 | S. P. CONSTRUCTION | 95.15 | 85.36 | 89.71 | 100
Total | [13 empty] | 100.94 | 85.36 | 84.57