## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08723 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Jashaikati Zone - II & its adjoining mouza water supply scheme in Baduria Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000066/2021-2022 | 1703/B.Ar.D | 30/09/2021 | 15/10/2021 | SIRCON ENGINEERING SERVICES | 4.7 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08723 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Ramchandra pur khas pur, Hugle and Keutsa Mouzas of Baduria Block from Jasikhati Zone-II & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000052/2021-2022 | 1709/B.Ar.D. | 01/10/2021 | 30/12/2021 | UTPAL CONSTRUCTION AND CO | 73.47 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08723 | Retrofitting | Repairing and Renovation of 02 ( two) nos Pump House and allied works at the site of Jasaikathi ( Zone-II ) W/S Scheme at Baduria block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000179/2021-2022 | 266/B.Ar.D | 18/02/2022 | 10/03/2022 | NEELAM ENTERPRISE | 4.72 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - II and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08723 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Akbar Biswas and others at Hugle under Jasaikathi - II W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000277/2021-2022 | 483/B.Ar.D | 16/03/2022 | 31/03/2022 | RHINE CONSTRUCTION | 4.72 | 0 | 0 | 1
Total | [13 empty] | 87.61 | 0 | 0