## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) | SM/08724 | Retrofitting | Eucalyptus bullah pilling, drum sheet walling including earth filling for protection of different dia UPVC/HDPE Pipeline near pond of Sumon Mondal under Jasaikathi - I W/S Scheme at Baduria block under JAL SWAPNA Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000267/2021-2022 | 477/B.Ar.D | 16/03/2022 | 31/03/2022 | M/S DATTA ENTERPRISE | 4.47 | 0 | 0 | 100
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Jashaikati Zone - I and Its Adjoining Mouzas Water Supply Scheme under Baduria Block for providing Functional House Tap Connection in North 24 Parganas under Barasat Arsenic Division PHE Dte (Phase- II) | SM/08724 | Retrofitting | Providing Functional House Hold Tap Connection and allied works at Jashaikati mouza of Baduria Block from Jashaikati ( Zone-I ) & Its Adjoining Mouzas Ground Water Supply Scheme Under '' JAL SWAPNA'' programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000123/2021-2022 | 2078/B.Ar.D. | 02/12/2021 | 02/03/2022 | KINGS & CO. | 117.37 | 0 | 0 | 100
Total | [13 empty] | 121.84 | 0 | 0