## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Route survey, distribution design & DPR preparation for providing FHTC (Functional Household Tap Connection) by retrofitting under Jal Swapna for Dwarir Jangle water supply scheme in Sandeshkhali - II Block of North 24 Pargana District under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000065/2021-2022 | 1702/B.Ar.D | 30/09/2021 | 15/10/2021 | SIRCON ENGINEERING SERVICES | 4.68 | 4.68 | 99.98 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Laying of UPVC Pipe at damaged portion at Karnakhali of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000153/2021-2022 | 2257/B.Ar.D | 30/12/2021 | 29/01/2022 | A P POWER AND CONCRETE | 4.12 | 4.12 | 99.87 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Laying of UPVC Pipe at damaged portion at Giri Para of Dwarir Jangal W/S scheme at Sandeshkhali Block- II for providing FHTC under Jalswapna Programme under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000151/2021-2022 | 2233/B.Ar.D | 28/12/2021 | 27/01/2022 | M/S L.P. CONSTRUCTION | 4.8 | 4.8 | 99.94 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Providing Functional House Hod Connection and Allied workas at 6 nos habitation of Dwarir Jangle Mouzas of Sandeshkhali II Block from Dwarir Jangle Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000054/2021-2022 | 1711/B.Ar.D. | 01/10/2021 | 30/12/2021 | A P POWER AND CONCRETE | 45.66 | 43.57 | 95.42 | 1
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Laying of UPVC Pipe at khulnaghat of Dwarirjangal W/S scheme at Sandeshkhali Block- II for providing FHTC under " JAL JIBAN MISSION" under Barasat Arsenic Division, PHE Dte. (SM/08725) (Sl No. 5) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000142/2022-2023 | 2125/B.Ar.D. | 04/11/2022 | 25/11/2022 | A P POWER AND CONCRETE | 4.83 | 4.83 | 100 | 1
6 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Dwarir Jangle Water Supply Scheme under Sandeshkhali - II Block for providing Functional House Tap Connection in North 24 Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08725 | Retrofitting | Protection of UPVC distribution pipe line at 7 no. Sarder Para of Dwarir Jungle W/S scheme at Sandeshkhali- II under Barasat Arsenic Division, P.H.E. Dte. (Length - 60 mtr. Approx) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000174/2022-2023 | 2483/B.Ar.D. | 21/12/2022 | 10/01/2023 | M/S ASHA ENGINEERING | 5.41 | 5.41 | 99.99 | 1
Total | [13 empty] | 69.51 | 67.41 | 96.98