## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | Retrofitting | Providing Functional House Hod Connection and Allied workas at Kamduni and Kharibari Mouzas of Barasat II Block from Mahisgadi & Its Adjoining Mouzas Ground Water Supply Scheme Under " Jal Swapna " Programme under Barasat Arsenic Division PHE, Dte. (Phase-II) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000053/2021-2022 | 1710/B.Ar.D. | 01/10/2021 | 30/12/2021 | BALAJEE ENTERPRISES | 51.31 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | Retrofitting | Emergent protection of UPVC distribution pipe line near Haroa Khal from Dilip Mondal House to Kharibari Purba para of Mahisgadi W/S scheme related to the work FHTCat Barasat - II under Barasat Arsenic Division, P.H.E. Dte. (Approx. Length = 70 mtr) | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000190/2021-2022 | 362/B.Ar.D | 03/03/2022 | 18/03/2022 | M/S B. B. ENGINEERING | 4.8 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | Retrofitting | Repairing & Renovation of damaged Ladder of OHR & allied works at Mahishgadi Water Supply Scheme under Barasat -II block under Barasat Arsenic Division, P.H.E. Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000218/2021-2022 | 337/B.Ar.D | 28/02/2022 | 15/03/2022 | BALAJEE ENTERPRISES | 4.63 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | Retrofitting | Repairing and renovation of 02 (two) nos pump house and 01 (one) no I.E.P room and allied works at the site of Mahisgadi W/S Scheme at Barasat - II block, North 24 Pgs. district under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000082/2021-2022 | 1732/B.Ar.D | 05/10/2021 | 04/11/2021 | SUN ENTERPRISE | 4.77 | 0 | 0 | 100
5 | NORTH 24 PARGANAS |  | Barasat Arsenic Division | Retrofitting of Mahisgadi water supply scheme under Barasat- II Block for providing Functional House Tap Connection in North 24Pargana District under Barasat Arsenic Division PHE Dte (Phase - II) | SM/08727 | Retrofitting | Emergent works of Development of Land, Protection of Pipe line and Road restoration due to laying of UPVC/HDPE Pipe line for providing FHTC of MAHISHGADI Water Supply Scheme under Barasat - II Block under Barasat Arsenic Division, PHE Dte. | Assistant Engineer, HQ-II, Barasat Arsenic Division | Junior Engineer | ORD/000054/2023-2024 | 1647/B.Ar.D. | 14/07/2023 | 28/08/2023 | BALAJEE ENTERPRISES | 24.37 | 0 | 0 | 100
Total | [13 empty] | 89.89 | 0 | 0